## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | Retrofitting | Additional Laying of distribution system at Terateri Mouza for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl.No-06) | AE | JE3 | ORD/000172/2022-2023 | 309/RSD | 08/09/2022 | 08/10/2022 | GOURANGA MONDAL | 4.98 | 4.98 | 99.9 | 50
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | Retrofitting | Additional laying of distribution system At Beja Village for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl. No-05) | AE | JE3 | ORD/000170/2022-2023 | 308/RSD | 08/09/2022 | 08/10/2022 | GOURANGA MONDAL | 4.95 | 4.95 | 99.89 | 50
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | Retrofitting | Providing FHTC from existing distribution system at Beja,Taratari,Chuatari & Selahat mouzas within Beja w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-03) | AE | JE3 | ORD/000168/2022-2023 | 306/RSD | 08/09/2022 | 08/10/2022 | GOURANGA MONDAL | 4.55 | 4.53 | 99.53 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. | SM/12657 | Retrofitting | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) | AE | JE3 | ORD/000169/2022-2023 | 307/RSD | 08/09/2022 | 08/10/2022 | GOURANGA MONDAL | 4.77 | 1.14 | 23.93 | 100
Total | [13 empty] | 19.26 | 15.6 | 81