## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Allied Functional Household Tap Connection from existing distribution system at different mouzas under Puranagram Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000262/2023-2024 | 3453/BHM | 03/08/2023 | 11/11/2024 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 80.63 | 0 | 0 | 65
2 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2023 to 30.04.2024) | AE(HQ) | JE | ORD/000431/2023-2024 | 4180/BHM | 31/10/2023 | 30/04/2024 | JAMSED ALI KHAN | 0.95 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2024 to 31.10.2024) | AE(HQ) | JE | ORD/000090/2024-2025 | 1373/BHM | 26/04/2024 | 26/10/2024 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Certified that entire quantity of HSD actually purchased and consumer for the purpose of office works as per context Log Book |  |  | BILL/01015/2023-2024 | BP-2023-24-483 | 27/03/2024 | 27/03/2024 | JAYRAM FILLING STATION | 0.48 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Certified that the total quantity of fuel supplied for the vehicle No. WB53B-8630 of Consumer for official purpose under Assistant Engineer (HQ) Birbhum Division for the month of Nov'23 and Dec'23 |  |  | BILL/00882/2023-2024 | BP-2023-24-422 | 07/03/2024 | 07/03/2024 | JAYRAM FILLING STATION | 0.48 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. | SM/12659 | Retrofitting | Continuation work for Supply of one no. Diesel-driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2024 to 30.04.2025) | AE(HQ) | Estimator | ORD/000436/2024-2025 | 2969/BHM | 30/10/2024 | 30/04/2025 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 100
Total | [13 empty] | 84.47 | 0 | 0