## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. | SM/12661 | Retrofitting | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000105/2023-2024 | 2059/BHM | 08/06/2023 | 17/07/2024 | SAPTADIP CONSTRUCTION | 54.29 | 36.03 | 66.36 | 91
Total | [13 empty] | 54.29 | 36.03 | 66.36