## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) | AE | JE3 | ORD/000433/2021-2022 | 24/BHM | 06/01/2022 | 07/03/2022 | SK ALIM | 75.03 | 0 | 0 | 97
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) | AE | JE3 | ORD/000480/2021-2022 | 279/BHM | 09/02/2022 | 10/04/2022 | PRADIP KUMAR SHARMA | 76.52 | 0 | 0 | 50
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | Retrofitting | Providing Left out FHTC for declaration of Swajal Gram Village at Raypur & Rupganj Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 01) | AE,AE(HQ) | JE1,JE3,JUNIOR ENGINEER | ORD/000163/2024-2025 | 451/RSD | 11/09/2024 | 26/09/2024 | GOURANGA MONDAL | 0.75 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | Retrofitting | Providing Left out FHTC for declaration of Swajal Gram Village at Gamira & Sehala Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 02) | AE,AE(HQ) | JE1,JE3,JUNIOR ENGINEER | ORD/000164/2024-2025 | 452/RSD | 11/09/2024 | 26/09/2024 | GOURANGA MONDAL | 0.68 | 0 | 0 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme | SM/12663 | Retrofitting | Providing Left out FHTC and allied work for declaration of Swajal Gram Village at Tajpur Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. -03) | AE,AE(HQ) | JE1,JE3,JUNIOR ENGINEER | ORD/000167/2024-2025 | 453/RSD | 11/09/2024 | 01/10/2025 | SOUMEN DAS | 0.97 | 0 | 0 | 100
Total | [13 empty] | 153.95 | 0 | 0