## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12666 | Retrofitting | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | AE | JE1 | ORD/000112/2022-2023 | 200/AE/NSD | 01/04/2022 | 16/05/2022 | M/S S.N CONSTRUCTION | 3.15 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | SM/12666 | Retrofitting | Extension of Pipeline along with FHTC at left out habitations of HARIDASPUR PWSS under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000059/2023-2024 | 1291/BHM | 18/04/2023 | 21/12/2025 | A.K. SIKDAR | 55.6 | 18.79 | 33.8 | 35
Total | [13 empty] | 58.74 | 18.79 | 31.99