## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. | SM/12667 | Retrofitting | Additional FHTC works along with Laying pipelines at different mouzas within Jhikadda W/S under Rampurhat Sub Division, Birbhum, Division, P.H.E Dte. | AE | JE1 | ORD/000314/2022-2023 | 2507/BHM | 17/11/2022 | 01/01/2023 | KAZI EMDADUL HAQUE | 12.78 | 0.28 | 2.17 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. | SM/12667 | Retrofitting | Additional laying of UPVC Pipe line for Maharapur, Routara, Mirpur diff mouzas for providing FHTC under JHIKADDA Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | AE | JE1 | ORD/000007/2023-2024 | 1086/BHM | 06/04/2023 | 05/06/2023 | KAZI ZAKIR HOSSAIN | 6.72 | 6.7 | 99.7 | 100
Total | [13 empty] | 19.5 | 6.98 | 35.78