## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 1587/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 8.06 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Providing Electro-mechanical accessories and others for Paikpara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000441/2023-2024 | 2100/Bol.MD | 22/08/2023 | 01/04/2025 | SATYAJIT GHOSH | 27.98 | 25.02 | 89.41 | 70
3 | BIRBHUM | Sainthia | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 28/02/2026 | SHREE J.M. CONSTRUCTION | 1236.08 | 173.9 | 14.07 | 54
4 | BIRBHUM | Sainthia | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Paikpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE | JE1 | ORD/000046/2025-2026 | 1510/BHM | 23/05/2025 | 21/08/2025 | SHREE J.M. CONSTRUCTION | 8.94 | 0 | 0 | 0
Total | [13 empty] | 1281.07 | 198.92 | 15.53