## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 1587/BHM | 26/04/2023 |  | Resource Division | 8.06 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Providing Electro-mechanical accessories and others for Paikpara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000441/2023-2024 | 2100/Bol.MD | 22/08/2023 | 21/10/2023 | SATYAJIT GHOSH | 27.98 | 20.63 | 73.72 | 70
3 | BIRBHUM | Sainthia | Birbhum Division | Paikpara Piped Water Supply Scheme. | SM/12669 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 29/04/2024 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 0 | 54
Total | [13 empty] | 1272.12 | 20.63 | 1.62