## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1375/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 34.3 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Name of Work: Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Deoash PWSS in the district of Birbhum, under P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000542/2024-2025 | 3801/BOL.MD | 12/09/2024 | 12/10/2024 | SATYAJIT GHOSH | 4.41 | 4.4 | 99.77 | 100
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | New service connection at Dewas PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02252/2023-2024 | BP-2023-24-316 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | New service connection at Dewas PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01027/2024-2025 | BP-24-25-278 | 06/12/2024 | 06/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.73 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 12/06/2025 | M/S. JAN MAHAMMAD | 1367.24 | 396.88 | 29.03 | 75
6 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Providing Electro-mechanical accessories and others for Deoash & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000414/2023-2024 | 2086/Bol.MD | 22/08/2023 | 02/04/2025 | SUNIL RABIDAS | 28.9 | 20.24 | 70.03 | 40
7 | BIRBHUM | Sainthia | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Repairing and renovation of existing Pump House, Chlorine room, Security guard room and Boundary wall for Deoash and Adjoining Mouzas PWSS Under Birbhum Division, P.H.E Dte. | AE | JE,JE1 | ORD/000064/2025-2026 | 1583/BHM | 02/06/2025 | 31/08/2025 | SUBHRADIP SARKAR | 18.7 | 0 | 0 | 0
Total | [13 empty] | 1465.69 | 421.53 | 28.76