## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1375/BHM | 24/04/2023 |  | Resource Division | 34.3 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Providing Electro-mechanical accessories and others for Deoash & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000414/2023-2024 | 2086/Bol.MD | 22/08/2023 | 21/10/2023 | SUNIL RABIDAS | 28.9 | 7.66 | 26.5 | 40
3 | BIRBHUM | Sainthia | Birbhum Division | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 07/01/2024 | M/S. JAN MAHAMMAD | 1367.24 | 280.07 | 20.48 | 45
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS | SM/12670 | New | New service connection at Dewas PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02252/2023-2024 | BP-2023-24-316 | 18/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | null
Total | [13 empty] | 1433.86 | 287.73 | 20.07