## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | Madhura and Adjoining mouzas PWSS | SM/12671 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1471/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 113.39 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS | SM/12671 | New | Providing Electro-mechanical accessories and others for MADHURA piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000932/2023-2024 | 3562/BOL.MD | 04/12/2023 | 02/02/2024 | INDRANI ENTERPRISE | 27.43 | 22.09 | 80.54 | 80
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS | SM/12671 | New | ,Operation and Guarding of pumping machinery and others at Madhura Piped Water supply Scheme (Pump House No-I(Block- Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte |  |  | ORD/000829/2024-2025 | 1077./AE-III | 29/07/2024 | 29/08/2024 | INDRANI ENTERPRISE | 0.3 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS | SM/12671 | New | Operation and Guarding of pumping machinery and others at Madhura Piped water supply scheme,(Pump House No-II)Block; Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte. |  |  | ORD/000825/2024-2025 | 1078./AE-III | 29/07/2024 | 29/08/2024 | INDRANI ENTERPRISE | 0.3 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS | SM/12671 | New | WBSEDCL QUOTATION FOR MODHURA W S P H NO I WS SCHEME |  |  | BILL/01778/2023-2024 | BP-23-24-239 | 29/01/2024 | 29/01/2024 | WBSEDCL | 2.79 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS | SM/12671 | New | WBSEDCL QUOTATION FOR MODHURA P H NO 2 |  |  | BILL/01712/2023-2024 | BP-23-24-238 | 29/01/2024 | 29/01/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-I | Birbhum Division | Madhura and Adjoining mouzas PWSS | SM/12671 | New | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000045/2023-2024 | 1173/BHM | 12/04/2023 | 01/01/2026 | SK ABDUL HALIM | 921.73 | 357.67 | 38.8 | 90
Total | [13 empty] | 1066.17 | 379.76 | 35.62