## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1429/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 15.61 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | Providing Electro-mechanical accessories and others for KANAIPUR piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000931/2023-2024 | 3561/BOL.MD | 04/12/2023 | 02/02/2024 | PRADIP KUMAR DHABAL | 27.77 | 25.83 | 93.03 | 90
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | WBSEDCL QUOTATION FOR KANAIPUR W S P H NO I WS SCHEME |  |  | BILL/01783/2023-2024 | BP-23-24-240 | 29/01/2024 | 29/01/2024 | WBSEDCL | 5.09 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | WBSEDCL QUOTATION FOR KANAIPUR P H NO.II WS SCHEME |  |  | BILL/01785/2023-2024 | BP-23-24-241 | 29/01/2024 | 29/01/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE2 | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 02/08/2025 | M/S GOUTAM DAS | 1594.34 | 357.04 | 22.39 | 28
6 | BIRBHUM | Nalhati-I | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS | SM/12672 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Kanaipur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000045/2025-2026 | 1507/BHM | 23/05/2025 | 21/08/2025 | M/S GOUTAM DAS | 41.79 | 0 | 0 | 10
Total | [13 empty] | 1684.81 | 382.87 | 22.72