## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1420/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 115.81 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Providing Electro-mechanical accessories and others for Nanubazar & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000428/2023-2024 | 2093/Bol.MD | 22/08/2023 | 01/07/2025 | ASHUTOSH DAS & CO. | 28.65 | 0 | 0 | 45
3 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 2490/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 9.46 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Nanubazar Piped Water Supply Scheme | SM/12673 | New | New service connection at Nanubazar PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01026/2024-2025 | BP-24-25-277 | 06/12/2024 | 06/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.13 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Sinking of 02(Two) nos. 200mm X 200 mm X 174m deep Tube Wells Fitted With M.S Housing & Well Pipe by Direct Rotary Rig for Nanubazar and Adjacent areas Piped Water Supply Scheme, Block:Sainthia under Birbhum Division, P.H.E Dte | AE | JE3 | ORD/000535/2024-2025 | 315/BHM | 28/01/2025 | 29/03/2025 | WATER TECH | 25.26 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Construction of, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house , 200 CuM, capacity O.H.R. , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NANUBAZAR & its adjoining mouzas water supply scheme within Sainthia Blocki ncluding supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE,JE2,JE3 | ORD/000129/2024-2025 | 2263/BHM | 14/08/2024 | 30/07/2026 | PRANAB KUMAR GHOSH | 366.36 | 0 | 0 | 20
7 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Nanubazar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE | JE1 | ORD/000089/2025-2026 | 1646/BHM | 12/06/2025 | 10/09/2025 | PRANAB KUMAR GHOSH | 49.37 | 0 | 0 | 0
Total | [13 empty] | 601.05 | 0 | 0