## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1420/BHM | 24/04/2023 |  | Resource Division | 115.81 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Providing Electro-mechanical accessories and others for Nanubazar & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000428/2023-2024 | 2093/Bol.MD | 22/08/2023 | 21/10/2023 | ASHUTOSH DAS & CO. | 28.65 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Construction of, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house , 200 CuM, capacity O.H.R. , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NANUBAZAR & its adjoining mouzas water supply scheme within Sainthia Blocki ncluding supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE,JE3 | ORD/000129/2024-2025 | 2263/BHM | 14/08/2024 | 14/08/2025 | PRANAB KUMAR GHOSH | 366.36 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | Nanubazar Piped Water Supply Scheme | SM/12673 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 2490/BHM | 03/09/2024 |  | Resource Division | 9.46 | 0 | 0 | 0
Total | [13 empty] | 520.28 | 0 | 0