## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 1365/BHM | 24/04/2023 |  | Resource Division | 12.93 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Providing Electro-mechanical accessories and others for Matiara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000420/2023-2024 | 2091/Bol.MD | 22/08/2023 | 21/10/2023 | CINZANO | 27.89 | 17.37 | 62.28 | 50
3 | BIRBHUM | Sainthia | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 12/01/2024 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 1.33 | 0.14 | 65
4 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | New service connection at Matiara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00174/2024-2025 | BP-24-25-90 | 19/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | null
5 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | New service connection at Matiara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00174/2024-2025 | BP-24-25-90 | 19/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | null
Total | [13 empty] | 1026.61 | 18.7 | 1.82