## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 1365/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 12.93 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Matiara PWSS in the district of Birbhum, under P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2024-2025 | 3872/BOL.MD | 19/09/2024 | 19/10/2024 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 4.35 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | New service connection at Matiara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00174/2024-2025 | BP-24-25-90 | 19/06/2024 | 19/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE,JE1 | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 26/03/2026 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 0 | 65
5 | BIRBHUM | Sainthia | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Providing Electro-mechanical accessories and others for Matiara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000420/2023-2024 | 2091/Bol.MD | 22/08/2023 | 14/09/2025 | CINZANO | 27.89 | 0 | 0 | 50
6 | BIRBHUM | Sainthia | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. | SM/12674 | New | Repairing of Pump House & construction of drain under Matiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE1,JE2 | ORD/000221/2025-2026 | 2141/BHM | 19/08/2025 | 17/11/2025 | BRAHMA CONSTRUCTION COMPANY | 17.25 | 0 | 0 | 0
Total | [13 empty] | 1044.73 | 0 | 0