## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Birbhum Division | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | SM/12675 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1382/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 16.97 | 0 | 0 | 0
2 | BIRBHUM | Suri-I | Bolpur Mechanical | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | SM/12675 | New | Providing Electro-mechanical accessories and others for Kamardangal PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000429/2023-2024 | 2104/BOL.MD. | 22/08/2023 | 21/10/2023 | M/S S.R. ENTERPRISE | 27.85 | 17.51 | 62.87 | 30
3 | BIRBHUM | Suri-I | Bolpur Mechanical | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | SM/12675 | New | WBSEDCL QUOTATION FOR PURBA KAMARDANGAL WS SCHEME |  |  | BILL/01788/2023-2024 | BP-23-24-242 | 29/01/2024 | 29/01/2024 | WBSEDCL | 6.19 | 0 | 0 | 0
4 | BIRBHUM | Suri-I | Birbhum Division | KAMARDANGAL PIPED WATER SUPPLY SCHEME. | SM/12675 | New | Different works for KAMAR DANGAL & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 02 | AE | JE,JE1 | ORD/000529/2022-2023 | 885/BHM | 21/03/2023 | 21/12/2023 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 208.71 | 91.79 | 43.98 | 80
Total | [13 empty] | 259.71 | 109.29 | 42.08