## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1519/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 17.4 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | New | Providing Electro-mechanical accessories and others for Andhargram PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000291/2023-2024 | 1497/Bol.MD | 17/07/2023 | 15/09/2023 | WEST BENGAL ENGINEERING CO. | 27.21 | 0 | 0 | 80
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | New | WBSEDCL QUOTATION FOR ANDHARGRAM P H NO 2 WS SCHEME |  |  | BILL/01450/2023-2024 | BP-23-24-174 | 07/12/2023 | 07/12/2023 | WBSEDCL | 3.65 | 0 | 0 | 0
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | New | WBSEDCL quotation for Andhargram ws scheme |  |  | BILL/01447/2023-2024 | BP-23-24-173 | 07/12/2023 | 07/12/2023 | WBSEDCL | 4.58 | 0 | 0 | 0
5 | BIRBHUM | Mohammad Bazar | Birbhum Division | ANDHARGRAM PIPED WATER SUPPLY SCHEME. | SM/12676 | New | Different works related to water supply scheme at ANDHARGRAM & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE(HQ) | JE | ORD/000031/2023-2024 | 1191/BHM | 12/04/2023 | 01/08/2024 | NISITH BARAN SARKAR | 255.87 | 0 | 0 | 65
Total | [13 empty] | 308.71 | 0 | 0