## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Providing FHTC including laying of distribution system within the command area of villages Jethia, Haridaspur, Jinderpur, Kapista. Gagha & Debogram,G.P - Bharkata, Kapista, Ganpur & Rampur, Block - Md.Bazar for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | AE | JE | ORD/000107/2023-2024 | 1732/BHM | 12/05/2023 | 11/07/2023 | HIMANGSU SEKHAR SARKAR | 78.36 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Rajganja, Hazrapur, Chinpai and Balijuri under Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE | ORD/000334/2022-2023 | 2605/BHM | 24/11/2022 | 23/01/2023 | RICK CONSTRUCTION | 78.18 | 30.86 | 39.47 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Asanjola, Bamnigao under Block Rampurhat- I for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE | ORD/000244/2022-2023 | 2585/BHM | 22/11/2022 | 22/12/2022 | INDRAJIT DUTTA. | 21.46 | 5.89 | 27.45 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Additional work for providing Balance FHTC including laying of distribution system for village Geruapahari JL NO 74,G.P Babuijore, Block- Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte. (Sl. No.8) | AE | JE | ORD/000472/2022-2023 | 222/BHM | 20/01/2023 | 06/03/2023 | MA KANKALI ENTERPRISE | 7.51 | 0.58 | 7.76 | 84
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Muktipur & Kuralmetia under Rajnagar Block for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000108/2023-2024 | 1725/BHM | 12/05/2023 | 26/06/2023 | BHABANI ENTERPRISE | 16.76 | 15.09 | 90.03 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Providing FHTC including laying of distribution system within the command area of villages Rajganja, Hajrapur, Chinpai & Balijuri , G.P - Parulia, Chinpai & Balijuri, Block - Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | AE | JE | ORD/000095/2023-2024 | 1647/BHM | 02/05/2023 | 16/06/2023 | RICK CONSTRUCTION | 28.38 | 28.37 | 99.95 | 43
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Raotara J.L No 76 , G.P Parulia , Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000211/2023-2024 | 3260/BHM | 26/07/2023 | 09/09/2023 | GOUTAM MONDAL | 3.02 | 2.82 | 93.2 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Sagarbhanga, J.L No 63, G.P Nakraconda, Block -Khoyrasole for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000412/2023-2024 | 4287/BHM | 10/11/2023 | 25/12/2023 | DATA CONSTRUCTION | 7.41 | 6.98 | 94.3 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Restoration of distribution pipe line (HDPE), Construction of Sluice Valve Chamber & concreting including FHTC for augmentation of Khayrasole (Zone-II) Piped Water Supply Scheme, Khayrasole Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000135/2024-2025 | 2154/BHM | 01/08/2024 | 15/09/2024 | RANJIT GHOSH | 4.57 | 4.55 | 99.7 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied work of Installation of Sluice Valve along with restoration of road and Land development at new OHR site under Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000140/2024-2025 | 2354/BHM | 22/08/2024 | 01/02/2025 | SK ALIM | 44.38 | 0 | 0 | 90
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Extension work of HDPE pipeline for providing FHTC of Kanakpur Mini W/S Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1,JE2 | ORD/000131/2024-2025 | 2160/BHM | 05/08/2024 | 19/09/2024 | BROTHERS ENTERPIRSE | 5.74 | 5.74 | 99.95 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied work of Laying Rising main including extension of pipeline with restoration of road for Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000139/2024-2025 | 2353/BHM | 22/08/2024 | 06/10/2024 | SK ALIM | 94.64 | 94.63 | 99.99 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied Work of Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Gaisara, J.L No 46, G.P Tantipara, Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JUNIOR ENGINEER | ORD/000588/2023-2024 | 752/BHM | 29/02/2024 | 14/04/2024 | AVIJIT CHANDA | 4.89 | 4.66 | 95.14 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Construction of 20 Nos Water Supply Overhead Structure at Different places under Draught Prone area at Dubrajpur Block (14 Nos.)and MD. Bazar (6 Nos) under RWS Birbhum Sub Division within Birbhum Division PHE Dte.. | AE | JE | ORD/000203/2023-2024 | 3163/BHM | 24/07/2023 | 28/02/2025 | PREMANANDA ROY BISWAS | 93.11 | 44.62 | 47.92 | 95
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Balance work of distribution pipeline including extension of pipeline for left out habitation (Purbo gopalpur)along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | AE | JE1,JE2 | ORD/000141/2024-2025 | 2415/BHM | 28/08/2024 | 27/10/2024 | SHIB GANGA CONSTRUCTION | 42.63 | 0 | 0 | 45
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Allied Works related to FHTC for village Putka JL No 04 G.P Lokepur Block Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte.( Sl. No.-05) | AE | JE,JE1,JUNIOR ENGINEER | ORD/000377/2024-2025 | 188/RWS | 21/11/2024 | 21/12/2024 | BHABANI ENTERPRISE | 0.95 | 0 | 0 | 90
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. | SM/12677 | Retrofitting | Sinking of Rig Bore Tubewell(DTH) method) at Adampur Village within Dubrajpur Dev. Block under 41 draught prone Village Scheme under Birbhum Division, PHE Dte. | AE | JE,JE3 | ORD/000455/2024-2025 | 3602/BHM | 31/12/2024 | 30/01/2025 | BHABATARAN SADHU | 5.34 | 0 | 0 | 95
Total | [13 empty] | 537.33 | 244.79 | 45.56