## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I,Murarai-II | Birbhum Division | Abdullahpur Piped Water Supply Scheme. | SM/12679 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1436/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 40.75 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. | SM/12679 | New | Supply and delivery of Submersible pump motor set for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. |  | Junior Engineer | ORD/000405/2024-2025 | 653/BMSD(D) | 02/09/2024 | 02/10/2024 | HINDOL ROY | 1.51 | 0 | 0 | 100
3 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. | SM/12679 | New | Supply and delivery of Al. armoured cable, Sluice Valve, NRV for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000406/2024-2025 | 654/BMSD(D) | 02/09/2024 | 02/10/2024 | SATYAJIT GHOSH | 2.55 | 2.55 | 100 | 100
4 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. | SM/12679 | New | Quotation deposit for empowering Abdullapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. |  |  | BILL/00979/2024-2025 | BP-2024-25-268 | 27/11/2024 | 27/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.97 | 0 | 0 | 0
5 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. | SM/12679 | New | Providing Electro-mechanical accessories and others for ABDULLAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000883/2023-2024 | 3287/Bol.MD | 29/09/2023 | 01/07/2025 | MENAKA ENTERPRISE | 41.33 | 0 | 0 | 65
Total | [13 empty] | 94.11 | 2.55 | 2.71