## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Asenga Piped Water Supply Scheme. | SM/12680 | New | Providing Electro-mechanical accessories and others for ASENGA and Adjoining moujas water supply scheme in Md Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000399/2023-2024 | 2078/BOL.MD. | 21/08/2023 | 20/10/2023 | UNIVERSAL ENTERPRISES | 28.8 | 0 | 0 | 70
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1433/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 95.69 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Different works related to water supply scheme at ASENGA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | Estimator | ORD/000069/2023-2024 | 1342/BHM | 20/04/2023 | 20/01/2024 | M/S GOUTAM DAS | 409.61 | 0 | 0 | 65
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA P H NO.I WS SCHEME |  |  | BILL/01449/2023-2024 | BP-23-24-172 | 07/12/2023 | 07/12/2023 | WBSEDCL | 6.71 | 0 | 0 | 0
5 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA TW-I (OHR SITE) |  |  | BILL/02251/2023-2024 |  | 14/03/2024 | 14/03/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
6 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Asenga Piped Water Supply Scheme. | SM/12680 | New | New Service connection at Asenga WSS, Block- Khoyrasole under Bolpur Mechanical Division, PHE Dte |  |  | BILL/02146/2023-2024 |  | 13/03/2024 | 13/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
7 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Asenga Piped Water Supply Scheme. | SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA PH NO.2 WS SCHEME |  |  | BILL/01452/2023-2024 | BP-23-24-171 | 07/12/2023 | 07/12/2023 | WBSEDCL | 3.82 | 0 | 0 | 0
8 | BIRBHUM | Mohammad Bazar | Birbhum Division | Asenga Piped Water Supply Scheme. | SM/12680 | New | Jack pushing for crossing PWD Road at different locations including all other allied works for Asenga piped Water Supply Scheme (Md.Bazar Development Block) under Birbhum Division P.H.E. Dte. | AE(HQ) | Estimator,JE | ORD/000687/2024-2025 | 863/BHM | 26/03/2025 | 09/06/2025 | M/S GOUTAM DAS | 65.5 | 0 | 0 | 40
Total | [13 empty] | 616.57 | 0 | 0