## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Bahadurpur Piped Water Supply Scheme. | SM/12681 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1529/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 23.48 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Bahadurpur Piped Water Supply Scheme. | SM/12681 | New | Quotation deposit for empowering Bahadurpur Water Supply Scheme P/H -I in Murarai CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00224/2024-2025 | BP-24-25-113 | 02/07/2024 | 02/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.61 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Birbhum Division | Bahadurpur Piped Water Supply Scheme. | SM/12681 | New | Different works related to water supply scheme at Bahadurpur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. Sl No 01 | AE | JE3 | ORD/000527/2022-2023 | 884/BHM | 21/03/2023 | 01/12/2025 | ABUL KALAM | 380.11 | 0 | 0 | 70
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Bahadurpur Piped Water Supply Scheme. | SM/12681 | New | Providing Electro-mechanical accessories and others for BAHADURPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000888/2023-2024 | 3291/Bol.M.D | 29/09/2023 | 01/04/2025 | SUNIL RABIDAS | 27.54 | 0 | 0 | 60
Total | [13 empty] | 434.74 | 0 | 0