## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I,Murarai-II | Birbhum Division | Chanchali piped water supply scheme. | SM/12683 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1487/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 157.22 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Chanchali piped water supply scheme. | SM/12683 | New | Quotation deposit for empowering Chanchali P/H-I Water Supply Scheme, Nandigram Kalitala in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00152/2024-2025 | BP-2024-2025-79 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Chanchali piped water supply scheme. | SM/12683 | New | Quotation deposit for Chanchali Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. |  |  | BILL/00826/2024-2025 | BP-24-25-180 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I,Murarai-II | Birbhum Division | Chanchali piped water supply scheme. | SM/12683 | New | Different works related to water supply scheme at Chanchali, Dakshin Kashila & Mahurapur and its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000081/2023-2024 | 1424/BHM | 25/04/2023 | 01/11/2024 | SUPRITI ENTERPRISE | 1680 | 0 | 0 | 30
5 | BIRBHUM | Murarai-I,Murarai-II | Bolpur Mechanical | Chanchali piped water supply scheme. | SM/12683 | New | Providing Electro-mechanical accessories and others for CHANCHALI piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000532/2023-2024 | 2173/Bol.MD | 01/09/2023 | 01/05/2025 | M/S. SREEJIT ENTERPRISE | 30.68 | 0 | 0 | 70
Total | [13 empty] | 1874.43 | 0 | 0