## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Dadpur Piped Water Supply Scheme. | SM/12684 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1537/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 31.16 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. | SM/12684 | New | Providing Electro-mechanical accessories and others for DADPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000886/2023-2024 | 3289/Bol.MD | 29/09/2023 | 21/11/2025 | QUAZI NOZRUL ISLAM | 27.77 | 21.62 | 77.86 | 60
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. | SM/12684 | New | Additional Quotation charges for Modification of Dadpur, Murarai CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00088/2024-2025 | BP-2024-2025-17 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.69 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. | SM/12684 | New | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.I WS SCHEME |  |  | BILL/01822/2023-2024 | BP-23-24-253 | 06/02/2024 | 06/02/2024 | WBSEDCL | 2.72 | 0 | 0 | 0
5 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. | SM/12684 | New | Quotation deposit for empowering Dadpur Water Supply Scheme P/H -III in Murarai CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00222/2024-2025 | BP-24-25-106 | 02/07/2024 | 02/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.7 | 0 | 0 | 0
6 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. | SM/12684 | New | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.II WS SCHEME |  |  | BILL/01824/2023-2024 | BP-23-24-254 | 06/02/2024 | 06/02/2024 | WBSEDCL | 2.7 | 0 | 0 | 0
7 | BIRBHUM | Murarai-I | Birbhum Division | Dadpur Piped Water Supply Scheme. | SM/12684 | New | Different works related to water supply scheme at DADPUR & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000555/2022-2023 | 839/BHM | 16/03/2023 | 01/08/2026 | NABIN DEBNATH | 315.84 | 205.01 | 64.91 | 80
Total | [13 empty] | 388.59 | 226.63 | 58.32