## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 1410/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 41.76 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | New | Providing Electro-mechanical accessories and others for Dakshin Chandipur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000986/2023-2024 | 3307/BOL.MD | 29/09/2023 | 28/09/2024 | PP CONCERN | 28.24 | 18.02 | 63.8 | 50
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | New | New service connection at Dakshin Chandipur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/01024/2024-2025 | BP-24-25-276 | 06/12/2024 | 06/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.1 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | New | Different works related to water supply scheme at DAKSHIN CHANDIPUR & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000073/2023-2024 | 1347/BHM | 20/04/2023 | 05/01/2026 | M/S KRIPASINDHU GHOSH & CO. | 427.17 | 0 | 0 | 50
5 | BIRBHUM | Sainthia | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. | SM/12685 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Dakshin Chandipur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE | JE1 | ORD/000077/2025-2026 | 1638/BHM | 11/06/2025 | 31/03/2026 | M/S KRIPASINDHU GHOSH & CO. | 43.46 | 0 | 0 | 80
Total | [13 empty] | 543.74 | 18.02 | 3.31