## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Dakshin Kasila Piped Water Supply Scheme. | SM/12686 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1442/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 16.44 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. | SM/12686 | New | Quotation deposit for empowering Dakshin Kashila P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00087/2024-2025 | BP-2024-2025-19 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.03 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. | SM/12686 | New | Quotation deposit for empowering Dakshin Kashila P/H-II Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00086/2024-2025 | BP-2024-2025-18 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. | SM/12686 | New | Providing Electro-mechanical accessories and others for DAKSHIN KASHILA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000887/2023-2024 | 3290/Bol.MD | 29/09/2023 | 01/04/2025 | S.K.ELECTRICALS | 30.47 | 0 | 0 | 65
Total | [13 empty] | 53.87 | 0 | 0