## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Providing Electro-mechanical accessories and others for Dakshin Madanpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000582/2023-2024 | 3385/Bol.MD | 16/10/2023 | 14/01/2024 | R. N. S. TRADING | 54.02 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 1391/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 32.83 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Supply delivery of voltage correction device at head work site of Dakshin Madanpur PWSS in the district of Birbhum, under P.H.E. Dte | Assistant Engineer-III | Junior Engineer | ORD/000532/2024-2025 | 3796/BOL.MD | 12/09/2024 | 12/10/2024 | M/S A.D.ENTERPRISE | 5.88 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 3260/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 6.91 | 0 | 0 | 0
5 | BIRBHUM | Dubrajpur | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Sinking of 250 X 200 mm Dia, 125 m deep tubewell, 5.90 m X 4.10 m Pump room / Chlorine room with sanitary arrangements, 8.00 m X 8.00 m Pump room / Chlorine room with sanitary arrangements, 150 CuM capacity O.H.R., 100 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at DAKSHIN MADANPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000317/2024-2025 | 3130/BHM | 18/11/2024 | 18/11/2025 | MALLICK CONSTRUCTION | 288.15 | 0 | 0 | 20
6 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. | SM/12687 | New | Supply delivery of voltage correction device at head work site of Augmentation of Ahmadpur (At Dakshin Madanpur) PWSS of Sainthia Block in the district of Birbhum, under P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000530/2024-2025 | 3795/BOL.MD | 12/09/2024 | 17/05/2025 | M/S SWAPAN BANERJEE | 15.07 | 0 | 0 | 80
Total | [13 empty] | 402.87 | 0 | 0