## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | New | Providing Electro-mechanical accessories and others for DHANANJAYPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000897/2023-2024 | 3292/Bol.MD | 29/09/2023 | 28/11/2023 | ABHISEK ENGTNEERING CONCERN | 27.4 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1443/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 20.68 | 0 | 0 | 0
3 | BIRBHUM | Murarai-I | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 2442/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 10.92 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. | SM/12688 | New | Sinking of 300 X 200 mm Dia (through) and 180 m deep tubewell , 02 nos, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Dhananjaypur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE2 | ORD/000101/2024-2025 | 2114/BHM | 29/07/2024 | 29/07/2026 | QUAZI SIRAJUL ISLAM | 435.37 | 0 | 0 | 1
Total | [13 empty] | 494.37 | 0 | 0