## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Dumugram piped water supply scheme. | SM/12689 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 2176/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 13.65 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Birbhum Division | Dumugram piped water supply scheme. | SM/12689 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 19/04/2026 | AKASH CONSTRUCTION | 1377.29 | 0 | 0 | 16
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dumugram piped water supply scheme. | SM/12689 | New | Providing Electro-mechanical accessories and others for DURUMGRAM piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000898/2023-2024 | 3293/Bol.MD | 29/09/2023 | 01/05/2025 | QUAZI NOZRUL ISLAM | 31.48 | 0 | 0 | 60
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Dumugram piped water supply scheme. | SM/12689 | New | Quotation deposit for empowering Dumurgram P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00085/2024-2025 | BP-2024-25-20 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.55 | 0 | 0 | 0
Total | [13 empty] | 1425.98 | 0 | 0