## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Ekpara Piped Water Supply Scheme. | SM/12690 | New | Different works related to water supply scheme at EKPARA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE1 | ORD/000157/2023-2024 | 2067/BHM | 08/06/2023 | 02/09/2024 | CHOWDHURY ENTERPRISE | 237.87 | 0 | 0 | 20
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Ekpara Piped Water Supply Scheme. | SM/12690 | New | Providing Electro-mechanical accessories and others for Ekpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000926/2023-2024 | 3531/Bol.MD | 29/11/2023 | 28/01/2024 | BIRBHUM ELECTRIC WORKS | 22.77 | 18.35 | 80.58 | 30
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Ekpara Piped Water Supply Scheme. | SM/12690 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1541/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 9.27 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Ekpara Piped Water Supply Scheme. | SM/12690 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 229/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 0.62 | 0 | 0 | 0
Total | [13 empty] | 270.53 | 18.35 | 6.78