## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Gaganpur piped water supply scheme. | SM/12691 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1451/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 76.79 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Birbhum Division | Gaganpur piped water supply scheme. | SM/12691 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 25/05/2024 | BENGAL ENGINEERING | 1204.06 | 0 | 0 | 30
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | Gaganpur piped water supply scheme. | SM/12691 | New | Providing Electro-mechanical accessories and others for GAGANPUR piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000544/2023-2024 | 2140/Bol.MD | 25/08/2023 | 26/06/2025 | MONI ELECTRICAL WORKS | 29.63 | 0 | 0 | 60
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | Gaganpur piped water supply scheme. | SM/12691 | New | Quotation deposit for empowering Gaganpur Water Supply Scheme P/H - I in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00089/2024-2025 | BP-2024-2025-41 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.13 | 0 | 0 | 0
Total | [13 empty] | 1313.61 | 0 | 0