## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - I | Birbhum Division | Harinduba Piped Water Supply Scheme. | SM/12692 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1570/BHM | 26/04/2023 |  | Resource Division | 27.14 | 0 | 0 | 0
2 | BIRBHUM | Murarai - I | Bolpur Mechanical | Harinduba Piped Water Supply Scheme. | SM/12692 | New | Providing Electro-mechanical accessories and others for HARINDUBA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000899/2023-2024 | 3294/Bol.MD | 29/09/2023 | 28/11/2023 | M/S SWAPAN BANERJEE | 27.4 | 0 | 0 | 0
3 | BIRBHUM | Murarai - I | Birbhum Division | Harinduba Piped Water Supply Scheme. | SM/12692 | New | Different related to water supply scheme at KHANPUR, Harinduba & Abdullahapur and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE3 | ORD/000074/2023-2024 | 1344/BHM | 20/04/2023 | 15/01/2024 | M/S ELLIUS KHAN | 1347.61 | 0 | 0 | 13
Total | [13 empty] | 1402.14 | 0 | 0