## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1517/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 13.34 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Birbhum Division | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 25/05/2024 | BENGAL ENGINEERING | 1204.06 | 75.31 | 6.25 | 30
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Quotation deposit for Kamarkhur Water Supply Scheme P/H-I in Paikar CCC under Bolpur Mechanical division, PHE Dte |  |  | BILL/00828/2024-2025 | BP-24-25-182 | 23/09/2024 | 23/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Providing Electro-mechanical accessories and others for KAMARKHUL piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000545/2023-2024 | 2141/Bol.MD | 25/08/2023 | 01/04/2026 | M. S. ENTERPRISE | 27.82 | 12.89 | 46.34 | 40
Total | [13 empty] | 1248.19 | 88.2 | 7.07