## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1517/BHM | 26/04/2023 |  | Resource Division | 13.34 | 0 | 0 | 0
2 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Providing Electro-mechanical accessories and others for KAMARKHUL piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000545/2023-2024 | 2141/Bol.MD | 25/08/2023 | 24/10/2023 | M. S. ENTERPRISE | 27.82 | 6.45 | 23.17 | 40
3 | BIRBHUM | Murarai - II | Birbhum Division | Kamarkhul Piped Water Supply Scheme. | SM/12693 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 21/05/2024 | BENGAL ENGINEERING | 1204.06 | 0 | 0 | 30
Total | [13 empty] | 1245.22 | 6.45 | 0.52