## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-I | Birbhum Division | Kamdebnala piped water supply scheme. | SM/12694 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1534/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 12.86 | 0 | 0 | 0
2 | BIRBHUM | Murarai-I | Birbhum Division | Kamdebnala piped water supply scheme. | SM/12694 | New | Different works related to water supply scheme at Kamdebnala & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000061/2023-2024 | 1302/BHM | 19/04/2023 | 01/11/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 282.44 | 124.64 | 44.13 | 42
3 | BIRBHUM | Murarai-I | Bolpur Mechanical | Kamdebnala piped water supply scheme. | SM/12694 | New | WBSEDCL QUOITATION FOR KAMDEBNALA PH NO-I |  |  | BILL/01839/2023-2024 | BP-2023-24-269 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.12 | 0 | 0 | 0
4 | BIRBHUM | Murarai-I | Bolpur Mechanical | Kamdebnala piped water supply scheme. | SM/12694 | New | Providing Electro-mechanical accessories and others for KAMDEBNALA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000900/2023-2024 | 3295/Bol.MD | 29/09/2023 | 02/12/2025 | M/S. UTTAM KUMAR CHATTERJEE | 25.93 | 17.32 | 66.77 | 90
Total | [13 empty] | 324.35 | 141.96 | 43.77