## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Lakshmi Narayanpur and Adjoining Mouzas PWSS | SM/12696 | New | Providing electro-mechanical accessories and others for Lakshmi Narayanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000385/2023-2024 | 1916/Bol.MD | 10/08/2023 | 10/08/2024 | S.P. CONSTRUCTION | 72.38 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Lakshmi Narayanpur and Adjoining Mouzas PWSS | SM/12696 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 1395/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 168.11 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Lakshmi Narayanpur and Adjoining Mouzas PWSS | SM/12696 | New | Supply Delivery & Installation of open well Sub-Mersable Pumping Machinery and allied electro-mechanical works at CWR under Lakshminarayanpur water supply scheme (Block-Nalhati-I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001171/2023-2024 | 298/AE-III | 22/02/2024 | 14/03/2024 | QUAZI NOZRUL ISLAM | 3.32 | 0 | 0 | 100
4 | BIRBHUM | Dubrajpur | Birbhum Division | Lakshmi Narayanpur and Adjoining Mouzas PWSS | SM/12696 | New | Different works related to water supply scheme at LAKSHMI NARAYANPUR & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE |  | ORD/000400/2023-2024 | 4176/BHM | 31/10/2023 | 31/07/2024 | APURBA MONDAL | 472.43 | 0 | 0 | 0
Total | [13 empty] | 716.24 | 0 | 0