## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | Majhara piped water supply scheme | SM/12698 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 1492/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 20.41 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Bolpur Mechanical | Majhara piped water supply scheme | SM/12698 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Majhara water supply scheme (Amdol Pump House-I) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001280/2023-2024 | 177/BMSD(D) | 18/03/2024 | 17/04/2024 | NITESH MANAGEMENT | 3.18 | 0 | 0 | 100
3 | BIRBHUM | Murarai-II | Birbhum Division | Majhara piped water supply scheme | SM/12698 | New | Different works related to water supply scheme at Majhara & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000062/2023-2024 | 1301/BHM | 19/04/2023 | 01/04/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 281.52 | 0 | 0 | 30
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | Majhara piped water supply scheme | SM/12698 | New | Providing Electro-mechanical accessories and others for MAJHARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000547/2023-2024 | 2143/Bol.MD | 25/08/2023 | 24/10/2023 | UNIVERSAL ENTERPRISES | 25.93 | 0 | 0 | 70
Total | [13 empty] | 331.04 | 0 | 0