## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Melanpur Piped Water Supply Scheme. | SM/12699 | New | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1411/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 19.04 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Melanpur Piped Water Supply Scheme. | SM/12699 | New | Providing Electro-mechanical accessories and others for Melanpur PWSS at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000442/2023-2024 | 2107/BOL.MD. | 22/08/2023 | 02/07/2025 | M/S. DILIP MITRA | 28.74 | 0 | 0 | 50
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Melanpur Piped Water Supply Scheme. | SM/12699 | New | New service connection at Melanpur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte |  |  | BILL/02239/2023-2024 | BP-2023-24-315 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.76 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Birbhum Division | Melanpur Piped Water Supply Scheme. | SM/12699 | New | Different works related to water supply scheme at MELANPUR & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE1 | ORD/000067/2023-2024 | 1340/BHM | 20/04/2023 | 01/01/2026 | BRAHMA CONSTRUCTION COMPANY | 412.68 | 0 | 0 | 37
Total | [13 empty] | 463.22 | 0 | 0