## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Metegaon and Adjoining Mouzas PWSS | SM/12700 | New | Providing Electro-mechanical accessories and others for Metegaon & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000580/2023-2024 | 3384/Bol.MD | 16/10/2023 | 14/01/2024 | SATYAJIT GHOSH | 52.86 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Metegaon and Adjoining Mouzas PWSS | SM/12700 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1398/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 114.57 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Metegaon and Adjoining Mouzas PWSS | SM/12700 | New | Acceptance cum Work Order for Supply and delivery of Sluice Valve for Metegaon and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | AE(HQ) | Estimator,JE1 | ORD/000638/2023-2024 | 949/BHM | 14/03/2024 | 13/04/2024 | SSPR VALVE MANUFACTURING PVT LTD | 9.2 | 9.2 | 100 | 100
4 | BIRBHUM | Dubrajpur | Birbhum Division | Metegaon and Adjoining Mouzas PWSS | SM/12700 | New | Different works related to water supply scheme at METEGAON & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE2,JE3 | ORD/000006/2023-2024 | 1085/BHM | 06/04/2023 | 01/05/2026 | M/S S.S. ENTERPRISE | 432.4 | 0 | 0 | 42
Total | [13 empty] | 609.03 | 9.2 | 1.51