## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Monai Piped Water Supply Scheme. | SM/12701 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 1419/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 20.44 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | Monai Piped Water Supply Scheme. | SM/12701 | New | Providing Electro-mechanical accessories and others for Monai & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000985/2023-2024 | 3308/BOL.MD | 29/09/2023 | 01/07/2025 | H.K.DAS & CO. | 28.74 | 0 | 0 | 75
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Monai Piped Water Supply Scheme. | SM/12701 | New | WBSEDCL QUOTATION FOR MONAI PH II WS SCHEME |  |  | BILL/02135/2023-2024 | BP-2023-24-296 | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Monai Piped Water Supply Scheme. | SM/12701 | New | WBSEDCL QUIOTATION FOR MONAI PH NO-I |  |  | BILL/01847/2023-2024 | BP-23-24-273 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.97 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | Monai Piped Water Supply Scheme. | SM/12701 | New | Different works related to water supply scheme at MONAI & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE1 | ORD/000078/2023-2024 | 1427/BHM | 25/04/2023 | 17/08/2025 | GHOSH ENTERPRISE | 316.44 | 0 | 0 | 80
6 | BIRBHUM | Sainthia | Birbhum Division | Monai Piped Water Supply Scheme. | SM/12701 | New | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Monai Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | AE | JE1,JE3 | ORD/000049/2025-2026 | 1512/BHM | 23/05/2025 | 21/08/2025 | GHOSH ENTERPRISE | 54.1 | 0 | 0 | 0
Total | [13 empty] | 427.14 | 0 | 0