## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 1372/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 15.09 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | New | Providing Electro-mechanical accessories and others for Bangjita & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000417/2023-2024 | 2089/Bol.MD | 22/08/2023 | 21/10/2023 | INDTECH ASSOCIATES | 28.7 | 18.08 | 62.99 | 50
3 | BIRBHUM | Sainthia | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | New | WBSEDCL QUOTATION BANGJITA PIPED WATER SUPPLY SCHEME. |  |  | BILL/01874/2023-2024 | BP-23-24-277 | 15/02/2024 | 15/02/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | New | Quotation deposit for Banjita Water Supply Scheme P/H-II in Suri East CCC under Bolpur Mechanical division, PHE Dte. |  |  | BILL/01010/2024-2025 | BP-24-25-271 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Birbhum Division | BANGJITA PIPED WATER SUPPLY SCHEME. | SM/12829 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 01/07/2025 | NAUTANDAS AND CO | 1377.28 | 92.71 | 6.73 | 35
Total | [13 empty] | 1432.76 | 110.79 | 7.73