## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Central Drilling | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000390/2022-2023 | 1430/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 8.69 | 82.81 | 0
2 | BIRBHUM | Sainthia | Central Drilling | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | PROVIDING DRILLIG CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000377/2022-2023 | 1431/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 8.79 | 83.81 | 0
3 | BIRBHUM | Sainthia | Birbhum Division | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 01/07/2025 | NAUTANDAS AND CO | 1377.28 | 56.08 | 4.07 | 35
4 | BIRBHUM | Sainthia | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | Providing Electro-mechanical accessories and others for Birsingha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000051/2023-2024 | 1058 | 08/06/2023 | 07/08/2023 | S.G.TECHNICAL SERVICES | 28.79 | 24.74 | 85.93 | 85
5 | BIRBHUM | Sainthia | Birbhum Division | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 1377/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 9.12 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | WBSEDCL QUOTATION FOR BIRSINGA PAHARPUR WS SCHEME |  |  | BILL/00705/2023-2024 | BP-2023-2024-62 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.3 | 0 | 0 | 0
7 | BIRBHUM | Sainthia | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. | SM/12830 | New | WBSEDCL QUOTATION FOR BIRSINGHA PAHARPUR P.H.NO.II |  |  | BILL/00706/2023-2024 | BP-2023-2024-61 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.3 | 0 | 0 | 0
Total | [13 empty] | 1440.77 | 98.3 | 6.82