## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1430/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 14.24 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000915/2023-2024 | 3542/BOL.MD | 30/11/2023 | 29/01/2024 | GOENKA ENTERPRISE | 30.69 | 0 | 0 | 60
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000002/2024-2025 | 685./AE-III | 08/04/2024 | 22/04/2024 | GOENKA ENTERPRISE | 1.58 | 0 | 0 | 100
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR |  |  | BILL/01575/2023-2024 | BP-23-24-208 | 04/01/2024 | 04/01/2024 | WBSEDCL | 0.44 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR |  |  | BILL/01574/2023-2024 | BP-23-24-209 | 04/01/2024 | 04/01/2024 | WBSEDCL | 3.26 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 01/10/2025 | SK ALIM | 1229.19 | 0 | 0 | 25
7 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.10.2024 to 31.12.2024.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. |  |  | ORD/000497/2024-2025 | 312/NSD | 30/09/2024 | 31/12/2024 | JOY CHAND MAL | 0.43 | 0 | 0 | 0
8 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Hiring of Swift Dizer (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub-Division under Birbhum Division, PHE Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & with effect from 01.02.2025 to 31.07.2025 | AE | JE1,JE2 | ORD/000598/2024-2025 | 40/NSD | 31/01/2025 | 31/07/2025 | JOY CHAND MAL | 0.85 | 0 | 0 | 0
9 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.01.2025 to 31.01.2025.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. |  |  | ORD/000536/2024-2025 | 429/NSD | 31/12/2024 | 31/01/2025 | JOY CHAND MAL | 0.15 | 0 | 0 | 0
10 | BIRBHUM | Nalhati-I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Jack pushing including Augur boring for extension of pipeline (DI & HDPE ) including supply of sluice valve with construction of valve chamber and restoration of Roads, pucca drain for KANIOR piped Water Supply Scheme (Nalhati-I Block) under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000447/2024-2025 | 3536/BHM | 23/12/2024 | 19/02/2025 | SK ALIM | 73.24 | 0 | 0 | 95
Total | [13 empty] | 1354.06 | 0 | 0