## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150 MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000384/2022-2023 | 1426/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 0 | 0 | 0
2 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000309/2022-2023 | 1427/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME, UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000513/2022-2023 | 1429/CDD | 29/11/2022 | 29/12/2022 | C.M. ENTERPRISE | 10.49 | 0 | 0 | 100
4 | BIRBHUM | Sainthia | Birbhum Division | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1480/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 24.21 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | WBSEDCL QUOTATION FOR DERPUR WS SCHEME |  |  | BILL/00703/2023-2024 | BP-2023-2024-56 | 02/08/2023 | 02/08/2023 | WBSEDCL | 3.31 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | QUOTATION BILL FOR DERPUR WS SCHEME |  |  | BILL/01353/2023-2024 | BP-23-24-149 | 28/11/2023 | 28/11/2023 | WBSEDCL | 5.48 | 0 | 0 | 0
7 | BIRBHUM | Sainthia | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Providing Electro-mechanical accessories and others for Derpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000775/2022-2023 | 313/Bol.MD | 24/03/2023 | 01/04/2025 | EMCON | 28.71 | 0 | 0 | 50
8 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000188/2023-2024 | 290/CMSD-I(D) | 18/12/2023 | 17/06/2024 | SUJATA BHOWMICK | 0.86 | 0 | 0 | 30
9 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-II), Block - Sainthia, Birbhum District under CDD , PHE Dte. | Driller In Charge | Junior Engineer | ORD/000533/2022-2023 | 495/CMSD-I | 28/09/2022 | 13/10/2022 | C.M. ENTERPRISE | 2.66 | 0 | 0 | 100
10 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-IV) , Block - Sainthia, Birbhum District under CDD , PHE Dte. | Driller In Charge | Junior Engineer | ORD/000531/2022-2023 | 493/CMSD-I | 28/09/2022 | 13/10/2022 | C.M. ENTERPRISE | 2.66 | 0 | 0 | 100
11 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-I), Block -Sainthia, Birbhum District under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000532/2022-2023 | 486/CMSD-I | 23/09/2022 | 08/10/2022 | C.M. ENTERPRISE | 4.18 | 0 | 0 | 100
12 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-II), Block Sainthia , Birbhum District under CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000534/2022-2023 | 487/CMSD-I | 23/09/2022 | 08/10/2022 | C.M. ENTERPRISE | 3.77 | 0 | 0 | 100
13 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-III) , Block-Sainthia, Birbhum District under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000535/2022-2023 | 488/CMSD-I | 23/09/2022 | 08/10/2022 | C.M. ENTERPRISE | 4.18 | 0 | 0 | 100
14 | BIRBHUM | Sainthia | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-IV), Block - Sainthia, Birbhum District under CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000530/2022-2023 | 494/CMSD-I | 28/09/2022 | 13/10/2022 | C.M. ENTERPRISE | 3.77 | 0 | 0 | 100
15 | BIRBHUM | Sainthia | Birbhum Division | DERPUR PIPED WATER SUPPLY SCHEME. | SM/12832 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE,JE1 | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 26/03/2026 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 0 | 65
Total | [13 empty] | 1094.07 | 0 | 0