## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | BHEJENA PIPED WATER SUPPLY SCHEME. | SM/12833 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1439/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 23.01 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | BHEJENA PIPED WATER SUPPLY SCHEME. | SM/12833 | New | Different works related to water supply scheme at BHEJENA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | Estimator | ORD/000098/2023-2024 | 1980/BHM | 05/06/2023 | 05/03/2024 | APURBA MONDAL | 205.69 | 0 | 0 | 50
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | BHEJENA PIPED WATER SUPPLY SCHEME. | SM/12833 | New | Providing Electro-mechanical accessories and others for Bhejena PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000584/2023-2024 | 3386/Bol.MD | 16/10/2023 | 15/12/2023 | INDTECH ASSOCIATES | 28.01 | 0 | 0 | 60
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | BHEJENA PIPED WATER SUPPLY SCHEME. | SM/12833 | New | Quotation deposit for Bhejena Water Supply Scheme P/H-I in Md Bazar CCC under Bolpur Mechanical division, PHE Dte |  |  | BILL/00900/2024-2025 | BP-24-25-236 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0 | 0
Total | [13 empty] | 263.37 | 0 | 0