## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Central Drilling | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X 200mm X 150Mtrs. depth) by utilising Departmental Machineries for Bhalian W/S Scheme (T/W-II) Sainthia Block under Birbum District, Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000495/2022-2023 | 1131/CDD | 04/11/2022 | 04/12/2022 | C.M. ENTERPRISE | 9.04 | 0 | 0 | 100
2 | BIRBHUM | Sainthia | Birbhum Division | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 1379/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 41.06 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | Providing Electro-mechanical accessories and others for Bhalian & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000416/2023-2024 | 2088/Bol.MD | 22/08/2023 | 01/07/2025 | MENAKA ENTERPRISE | 28.76 | 0 | 0 | 80
4 | BIRBHUM | Sainthia | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | WBSEDCL QUIOTATION FOR BHALIAN PH NO-I |  |  | BILL/01848/2023-2024 | BP-23-24-274 | 15/02/2024 | 15/02/2024 | WBSEDCL | 0.96 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | WBSEDCL QUOTATION FOR BHALIAN PWSS PUMP HOUSE NO-II |  |  | BILL/02131/2023-2024 | BP-2023-24-294 | 20/03/2024 | 20/03/2024 | WBSEDCL | 4.72 | 0 | 0 | 0
6 | BIRBHUM | Sainthia | Birbhum Division | BHALIAN PIPED WATER SUPPLY SCHME. | SM/12834 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 01/07/2025 | NAUTANDAS AND CO | 1377.28 | 0 | 0 | 35
Total | [13 empty] | 1461.81 | 0 | 0