## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1573/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 10.89 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Different works related to water supply scheme at Chauti & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000537/2022-2023 | 674/BHM | 01/03/2023 | 31/10/2025 | QUAZI SIRAJUL ISLAM. | 365.44 | 187.17 | 51.22 | 40
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Quotation deposit for empowering Chauti P/H-II Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00149/2024-2025 | BP-2024-2025-75 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Quotation deposit for empowering Chauti P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00153/2024-2025 | BP-2024-2025-76 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.82 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chember for Chaiti piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000070/2025-2026 | 1594/BHM | 03/06/2025 | 01/09/2025 | QUAZI SIRAJUL ISLAM | 96.35 | 0 | 0 | 0
Total | [13 empty] | 478.41 | 187.17 | 39.12