## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1573/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 10.89 | 0 | 0 | 0
2 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Different works related to water supply scheme at Chauti & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000537/2022-2023 | 674/BHM | 01/03/2023 | 01/04/2026 | QUAZI SIRAJUL ISLAM. | 365.44 | 0 | 0 | 40
3 | BIRBHUM | Murarai-II | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Quotation deposit for empowering Chauti P/H-II Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00149/2024-2025 | BP-2024-2025-75 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Quotation deposit for empowering Chauti P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00153/2024-2025 | BP-2024-2025-76 | 13/06/2024 | 13/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.82 | 0 | 0 | 0
5 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chember for Chaiti piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000070/2025-2026 | 1594/BHM | 03/06/2025 | 01/09/2025 | QUAZI SIRAJUL ISLAM | 96.35 | 0 | 0 | 0
6 | BIRBHUM | Murarai-II | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Providing Electro-mechanical accessories and others for Chauti PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000941/2023-2024 | 3302/BOL.MD | 29/09/2023 | 31/07/2025 | MONI ELECTRICAL WORKS | 27.59 | 0 | 0 | 60
7 | BIRBHUM | Murarai-II | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. | SM/12835 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 573.84 | 0 | 0