## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1415/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 6.36 | 0 | 0 | 0
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | Providing Electro-mechanical accessories and others for Paikpara PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000905/2023-2024 | 3538/BOL.MD | 30/11/2023 | 01/06/2025 | BIRBHUM ELECTRIC WORKS | 27.38 | 0 | 0 | 70
3 | BIRBHUM | Nalhati-I | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.04.2024 to 30.09.2024. | AE | JE2 | ORD/000699/2023-2024 | 57/NSD | 14/03/2024 | 13/09/2024 | JOY CHAND MAL | 0.86 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | New service connection at Paikpara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02245/2023-2024 | BP-2023-24-314 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.79 | 0 | 0 | 0
5 | BIRBHUM | Nalhati-I | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | New service connection at Paikpara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02244/2023-2024 | BP-2023-24-313 | 18/03/2024 | 18/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-I | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO II WS SCHEME |  |  | BILL/01781/2023-2024 | BP-23-24-244 | 29/01/2024 | 29/01/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-I | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO I WS SCHEME |  |  | BILL/01780/2023-2024 | BP-23-24-243 | 29/01/2024 | 29/01/2024 | WBSEDCL | 6.08 | 0 | 0 | 0
8 | BIRBHUM | Nalhati-I | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. | SM/12836 | New | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000045/2023-2024 | 1173/BHM | 12/04/2023 | 01/01/2026 | SK ABDUL HALIM | 921.73 | 0 | 0 | 90
Total | [13 empty] | 971.37 | 0 | 0