## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai-II | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-I , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000449/2022-2023 | 1379/CDD | 24/11/2022 | 24/12/2022 | OSMAN SEKH | 10.67 | 8.27 | 77.51 | 100
2 | BIRBHUM | Murarai-II | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-II , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000448/2022-2023 | 1380/CDD | 24/11/2022 | 24/12/2022 | OSMAN SEKH | 10.67 | 8.27 | 77.51 | 100
3 | BIRBHUM | Murarai-II | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1491/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 53.18 | 0 | 0 | 0
4 | BIRBHUM | Murarai-II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing Electro-mechanical accessories and others for Jijigram PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000389/2023-2024 | 1928/Bol.MD | 11/08/2023 | 10/10/2023 | SUNIL RABIDAS | 27.41 | 26.85 | 97.96 | 100
5 | BIRBHUM | Murarai-II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.I WS SCHEME |  |  | BILL/01471/2023-2024 | BP-23-24-193 | 14/12/2023 | 14/12/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
6 | BIRBHUM | Murarai-II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.II WS SCHEME |  |  | BILL/01470/2023-2024 | BP-23-24-194 | 14/12/2023 | 14/12/2023 | WBSEDCL | 3.14 | 0 | 0 | 0
7 | BIRBHUM | Murarai-II | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 01/03/2026 | SUNIL RABI DAS | 1250.5 | 405.34 | 32.41 | 60
Total | [13 empty] | 1359.14 | 448.74 | 33.02